## d7-enabled-modules-for-migration
Package	Name	Version	Analysis	Action	Reference
Administration	Actions permissions (VBO) (actions_permissions)	7.x-3.5	part of vbo	none
Administration	Administration menu (admin_menu)	7.x-3.0-rc5	now admin toolbar	none - in installation profile
Administration	Administration menu Toolbar style (admin_menu_toolbar)	7.x-3.0-rc5	now admin toolbar	none - in installation profile
Administration	Administration views (admin_views)	7.x-1.6	d8 core
Administration	Content type overview (content_type_overview)	7.x-1.0-beta2	no candidate in d8	none - not needed
Administration	Menu Admin per Menu (menu_admin_per_menu)	7.x-1.1	update available	UPGRADE
Administration	Module filter (module_filter)	7.x-2.0	update available	UPGRADE
Administration	Module Missing Message Fixer (module_missing_message_fixer)	7.x-1.2	update available	UPGRADE
Chaos tool suite	Bulk Export (bulk_export)	7.x-1.12	no candidate in d8	review after migration
Chaos tool suite	Chaos tools (ctools)	7.x-1.12	ctools available in d8	review b4 migration - is ctools needed now?
Chaos tool suite	Custom content panes (ctools_custom_content)	7.x-1.12	ctools available in d8	review b4 migration - is ctools needed now?
Chaos tool suite	Page manager (page_manager)	7.x-1.12	in beta in d8	review b4 migration - is page manager needed now?
Chaos tool suite	Views content panes (views_content)	7.x-1.12	no candidate in d8	review b4 migration	https://www.reddit.com/r/drupal/comments/6y8ghh/views_content_panes_in_d8/
Context	Context (context)	7.x-3.10	in beta in d8	UPGRADE
Context	Context layouts (context_layouts)	7.x-3.10	part of context	none
Context	Context UI (context_ui)	7.x-3.10	part of context	none
Core	Block (block)	7.65	d8 core	none - in installation profile
Core	Color (color)	7.65	d8 core	none - in installation profile
Core	Comment (comment)	7.65	d8 core	none - in installation profile
Core	Contextual links (contextual)	7.65	d8 core	none - in installation profile
Core	Database logging (dblog)	7.65	d8 core	none - in installation profile
Core	Field (field)	7.65	d8 core	none - in installation profile
Core	Field SQL storage (field_sql_storage)	7.65	d8 core	none - no longer separately listed
Core	Field UI (field_ui)	7.65	d8 core	none - in installation profile
Core	File (file)	7.65	d8 core	none - in installation profile
Core	Filter (filter)	7.65	d8 core	none - in installation profile
Core	Help (help)	7.65	d8 core	none - in installation profile
Core	Image (image)	7.65	d8 core	none - in installation profile
Core	List (list)	7.65	d8 core	none - no longer separately listed
Core	Locale (locale)	7.65	d8 core	none - no longer separately listed
Core	Menu (menu)	7.65	d8 core	none - in installation profile
Core	Node (node)	7.65	d8 core	none - in installation profile
Core	Number (number)	7.65	d8 core	none - no longer separately listed
Core	Options (options)	7.65	d8 core	none - in installation profile
Core	Overlay (overlay)	7.65	no candidate in d8	obsolete
Core	Path (path)	7.65	d8 core	none - in installation profile
Core	RDF (rdf)	7.65	d8 core	none - in installation profile
Core	Search (search)	7.65	d8 core	none - in installation profile
Core	Shortcut (shortcut)	7.65	d8 core	none - in installation profile
Core	System (system)	7.65	d8 core	none - in installation profile
Core	Taxonomy (taxonomy)	7.65	d8 core	none - in installation profile
Core	Text (text)	7.65	d8 core	none - in installation profile
Core	Update manager (update)	7.65	d8 core	none - in installation profile
Core	User (user)	7.65	d8 core	none - in installation profile
Custom breadcrumbs	Custom breadcrumbs (custom_breadcrumbs)	7.x-2.0-beta1	no candidate in d8	review after migration
Custom breadcrumbs	Custom breadcrumbs for paths (custom_breadcrumbs_paths)	7.x-2.0-beta1	no candidate in d8	review after migration
Date/Time	Date (date)	7.x-2.9	datetime is enabled in d8	review after migration
Date/Time	Date All Day (date_all_day)	7.x-2.9	in beta in d8	UPGRADE
Date/Time	Date API (date_api)	7.x-2.9	d8 core	none - no longer separately listed
Date/Time	Date Popup (date_popup)	7.x-2.9	update available	UPGRADE
Date/Time	Date Views (date_views)	7.x-2.9	datetime is enabled in d8	review after migration
Display Suite	Display Suite (ds)	7.x-2.15	update available	UPGRADE
Display Suite	Display Suite Extras (ds_extras)	7.x-2.15	update available	UPGRADE
Display Suite	Display Suite Format (ds_format)	7.x-2.15	update available	UPGRADE
Display Suite	Display Suite Forms (ds_forms)	7.x-2.15	update available	UPGRADE
Display Suite	Display Suite Search (ds_search)	7.x-2.15	update available	UPGRADE
Display Suite	Display Suite UI (ds_ui)	7.x-2.15	update available	UPGRADE
ECK	Entity Construction Kit (eck)	7.x-2.0-rc7	d8 core	none - no longer separately listed
Entityqueue	Entityqueue (entityqueue)	7.x-1.1	in beta in d8	UPGRADE
Features	Downloads (downloads)		?	review after migration
Features	Features (features)	7.x-2.10	?	review after migration
Features	Landing Page Advanced (landing_page_advanced)		?	review after migration
Features	Large Slide (large_slide)		?	review after migration
Features	Large Slide Image Style (large_slide_image_style)		?	review after migration
Features	Link Tile (link_tile)		?	review after migration
Features	Slide (slide)		?	review after migration
Features	Slide Styles (slide_styles)		?	review after migration
Features	Slideshow View (slideshow_view)		?	review after migration
Fields	Address Field (addressfield)	7.x-1.0	replaced by ‘address’ module	INSTALL
Fields	Address Field Tokens (addressfield_tokens)	7.x-1.5	perhaps part of ‘address’ in d8?	review b4 migration - is this needed?
Fields	Advanced Link (advanced_link)	7.x-1.3	no candidate in d8	review after migration
Fields	Email (email)	7.x-1.3	basic email in d8 core - no separate module available	no candidate in d8	review after migration
Fields	Entity Reference (entityreference)	7.x-1.5	in d8 core	no candidate in d8	review after migration
Fields	Entity reference prepopulate (entityreference_prepopulate)	7.x-1.5	no candidate in d8	review after migration	potentially use ‘prepopulate’ in d8 if needed
Fields	Entity Reference View Widget (entityreference_view_widget)	7.x-2.0-rc5	no candidate in d8	review after migration
Fields	Field Group (field_group)	7.x-1.5	rc in d8	UPGRADE
Fields	Link (link)	7.x-1.6	d8 core	none - in installation profile
Fields	View reference (viewreference)	7.x-3.5	no candidate in d8	review after migration	potential replacement - viewfield
Filter	simplehtmldom API (simplehtmldom)	7.x-1.12	obsolete	obsolete
FlexSlider	FlexSlider (flexslider)	7.x-2.0-alpha3	in beta in d8	UPGRADE
FlexSlider	FlexSlider Fields (flexslider_fields)	7.x-2.0-alpha3	in beta in d8	UPGRADE
FlexSlider	FlexSlider Views Style (flexslider_views)	7.x-2.0-alpha3	in beta in d8	UPGRADE
Image	Manual Crop (manualcrop)	7.x-1.5	no candidate in d8	review after migration	potential replacement - image_widget_crop
Image	SmartCrop (smartcrop)	7.x-1.0-beta2	no candidate in d8	review after migration
Mail	SMTP Authentication Support (smtp)	7.x-1.7	do we still need this?	review after migration
Media	File entity (file_entity)	7.x-2.0-beta1+30-dev	should we convert file to media?	review b4 migration	https://www.drupal.org/project/migrate_file_to_media
Media	IMCE (imce)	7.x-1.9	update available	UPGRADE
Media	Media (media)	7.x-2.19	largely in core in d8	review after migration
Media	Media Internet Sources (media_internet)	7.x-2.19	submodule of above	review after migration
Media	Media WYSIWYG (media_wysiwyg)	7.x-2.19	submodule of above	review after migration
Media	Media: Vimeo (media_vimeo)	7.x-2.1	submodule of above	review after migration
Media	Media: YouTube (media_youtube)	7.x-3.0	submodule of above	review after migration
Media	Video Embed Field (video_embed_field)	7.x-2.0-beta11	update available	UPGRADE
OAuth	OAuth (oauth_common)	7.x-3.4	not needed?	review b4 migration
Other	Add to Cal (addtocal)	7.x-1.0	no candidate in d8	review b4 migration
Other	Advanced help (advanced_help)	7.x-1.1	alpha available in d8 - not needed?	review b4 migration
Other	Backup and Migrate (backup_migrate)	7.x-2.8	update available	UPGRADE
Other	Block Class (block_class)	7.x-2.3	in place	none - in installation profile
Other	Breakpoints (breakpoints)	7.x-1.3	not needed?	review b4 migration
Other	Checklist API (checklistapi)	7.x-1.2	not needed?	review b4 migration
Other	Diff (diff)	7.x-3.2	not needed?	review b4 migration
Other	Easy Social (easy_social)	7.x-2.11	not needed?	review b4 migration
Other	Entity API (entity)	7.x-1.9	largely in core in d8	review after migration
Other	Entity tokens (entity_token)	7.x-1.9	submodule of above	review after migration
Other	EU Cookie Compliance (eu_cookie_compliance)	7.x-1.28	update available	UPGRADE
Other	Eventbrite field (eventbritefield)	7.x-2.0-alpha3	no candidate in d8	review b4 migration
Other	Field as Block (fieldblock)	7.x-1.4	alpha available in d8 - not needed?	review b4 migration
Other	Field formatter conditions (ffc)	7.x-1.0-beta2	no candidate in d8	review b4 migration
Other	Field formatter settings API (field_formatter_settings)	7.x-1.1	submodule of above	review after migration
Other	FitVids (fitvids)	7.x-1.17	do we still need this?	review b4 migration	upgrade DOES exist if needed
Other	Libraries (libraries)	7.x-2.2	d8 core	-
Other	Linked Field (linked_field)	7.x-1.10	update available	UPGRADE
Other	Masquerade (masquerade)	7.x-1.0-rc7	in place	none - in installation profile
Other	Menu Block (menu_block)	7.x-2.5	update available	UPGRADE
Other	Noggin (noggin)	7.x-1.1	no candidate in d8	review b4 migration
Other	Pathauto (pathauto)	7.x-1.3	in place	none - in installation profile
Other	Rabbit Hole (rabbit_hole)	7.x-2.25	in beta in d8	UPGRADE
Other	Rabbit Hole nodes (rh_node)	7.x-2.25	submodule of above	review after migration
Other	Rabbit Hole taxonomy terms (rh_taxonomy)	7.x-2.25	submodule of above	review after migration
Other	Redirect (redirect)	7.x-1.0-rc3	update available	UPGRADE
Other	Role delegation (role_delegation)	7.x-1.1	update available	UPGRADE
Other	Scheduler (scheduler)	7.x-1.3	update available	UPGRADE
Other	Selective Tweets (selective_tweets)	7.x-2.3	no candidate in d8	review b4 migration
Other	Site map (site_map)	7.x-1.2	update available	UPGRADE AS ‘SITEMAP’	name changed
Other	Site Verification (site_verify)	7.x-1.2	no candidate in d8	review b4 migration
Other	Strongarm (strongarm)	7.x-2.0	not needed	-
Other	Style guide (styleguide)	7.x-1.1	not needed	-
Other	Token (token)	7.x-1.5	update available	UPGRADE
Panels	Panel nodes (panels_node)	7.x-3.8	not needed?	review b4 migration
Panels	Panelizer (panelizer)	7.x-3.4	not needed?	review b4 migration
Panels	Panels (panels)	7.x-3.8	not needed?	review b4 migration
Panels	Panels In-Place Editor (panels_ipe)	7.x-3.8	not needed?	review b4 migration
Paragraphs	Paragraphs (paragraphs)	7.x-1.0-rc5	in place	none - in installation profile
Picture	Picture (picture)	7.x-2.11	no candidate in d8	review b4 migration
Rules	Rules (rules)	7.x-2.8	alpha available in d8 - not needed?	review b4 migration
Rules	Rules UI (rules_admin)	7.x-2.8	submodule of above	review after migration
Sereno field bases	Sereno field bases - core (sereno_field_bases_core)		hope this migrates okay	review after migration
Sereno general	Sereno text formats & WYSIWYG profiles (sereno_text_formats_wysiwyg_profiles)		hope this migrates okay	review after migration
Sereno general	Sereno video support (sereno_video_support)		hope this migrates okay	review after migration
Sereno image styles	Sereno image styles - core (sereno_image_styles_core)		hope this migrates okay	review after migration
Sereno Modules	Sereno Glue Module (glue)		hope this migrates okay	review after migration
Sereno paragraphs bundles	Sereno paragraphs bundle - image (sereno_paragraphs_bundle_image)		hope this migrates okay	review after migration
Sereno paragraphs bundles	Sereno paragraphs bundle - quotation (sereno_paragraphs_bundle_quotation)		hope this migrates okay	review after migration
Sereno paragraphs bundles	Sereno paragraphs bundle - text block (sereno_paragraphs_bundle_text_block)		hope this migrates okay	review after migration
Sereno paragraphs bundles	Sereno paragraphs bundle - video (sereno_paragraphs_bundle_video)		hope this migrates okay	review after migration
SoundCloud	SoundCloud field (soundcloudfield)	7.x-1.4	in alpha in d8	UPGRADE
Spam control	CAPTCHA (captcha)	7.x-1.5	in beta in d8	UPGRADE
Spam control	Honeypot (honeypot)	7.x-1.17	update available	UPGRADE
Spam control	Image CAPTCHA (image_captcha)	7.x-1.5	submodule of captcha	-
Statistics	Facebook Tracking Pixel (facebook_tracking_pixel)	7.x-1.1	only dev branch in d8	review b4 migration
Statistics	Google Analytics (googleanalytics)	7.x-2.3	abandoned in d7, nothing it d8	review b4 migration
User interface	Accordion menu (accordion_menu)	7.x-1.2	no candidate in d8	review b4 migration
User interface	CKEditor Link (ckeditor_link)	7.x-2.3	no candidate in d8	review b4 migration
User interface	jQuery plugins (jquery_plugin)	7.x-1.0	obsolete	-
User interface	jQuery Update (jquery_update)	7.x-2.7	obsolete	-
User interface	Responsive Menus (responsive_menus)	7.x-1.7	not needed?	review b4 migration
User interface	Superfish (superfish)	7.x-1.9	not needed?	review b4 migration
User interface	Wysiwyg (wysiwyg)	7.x-2.2	not needed?	review b4 migration
User interface	Wysiwyg Linebreaks (wysiwyg_linebreaks)	7.x-1.6	not needed?	review b4 migration
UUID	Universally Unique ID (uuid)	7.x-1.2	in d8 core	no candidate in d8
Variable	Variable (variable)	7.x-2.5	no candidate in d8	review b4 migration
Views	Better Exposed Filters (better_exposed_filters)	7.x-3.4	in alpha in d8	UPGRADE
Views	Eva (eva)	7.x-1.2	in rc in d8	review b4 migration	do we need this? Probably have to rebuild it in more d8 fashion?
Views	Views (views)	7.x-3.21	in core in d8	-
Views	Views Bulk Operations (views_bulk_operations)	7.x-3.5	in place	none - in installation profile
Views	Views Distinct (views_distinct)	7.x-1.0	not needed? Nothing in d8	review b4 migration
Views	Views Slideshow (views_slideshow)	7.x-3.1	available in d8, but do we need it?	review b4 migration
Views	Views UI (views_ui)	7.x-3.21	-	-
Webform	Webform (webform)	7.x-4.19	update available	UPGRADE
XML sitemap	XML sitemap (xmlsitemap)	7.x-2.4	in alpha in d8	UPGRADE
XML sitemap	XML sitemap engines (xmlsitemap_engines)	7.x-2.4	submodule of above	-
XML sitemap	XML sitemap node (xmlsitemap_node)	7.x-2.4	submodule of above	-